## Sep05-Sep09
Daily Stand-up Meeting Report
Week: Sep05-Sep09
Project Name: Campus Cruise
Team Name: Crazy Coders
| Monday | Tuesday | Wednesday | Thursday | Friday
Nayan Reddy Prodduturi | 1) Shared contact information within the group. | 1) First Group Meeting. | 1) Discussed about team roles. | 1) Discussed about group meeting | 1) Conducted group meeting and discussed questions for the client.
| 2) Initiated first team meeting. | 2) Discussed about group roles. | 2) Discussed about group meeting project. | 2) Discussed about questions for the client. | 2) Client Meeting
| 3) We discussed what actually a campus tour means. | 3) We discussed about the basic requirements for the application | 3) We discussed about the basic requirements for the application | 3) We discussed how the application should work. | 3) No issues were arised.
Mallikharjuna Rao Dande | 1) Shared contact information within the group. | 1) First Group Meeting. | 1) Discussed about team roles. | 1) Discussed about group meeting | 1) Conducted group meeting and discussed questions for the client.
| 2) Initiated first team meeting. | 2) Discussed about group roles. | 2) Discussed about group meeting project. | 2) Discussed about questions for the client. | 2) Client Meeting
| 3) We discussed what actually a campus tour means. | 3) We discussed about the basic requirements for the application | 3) We discussed about the basic requirements for the application | 3) We discussed how the application should work. | 3) No issues were arised.
Chiranjeevi Sneha Kotu | 1) Shared contact information within the group. | 1) First Group Meeting. | 1) Discussed about team roles. | 1) Discussed about group meeting | 1) Conducted group meeting and discussed questions for the client.
| 2) Initiated first team meeting. | 2) Discussed about group roles. | 2) Discussed about group meeting project. | 2) Discussed about questions for the client. | 2) Client Meeting
| 3) We discussed what actually a campus tour means. | 3) We discussed about the basic requirements for the application | 3) We discussed about the basic requirements for the application | 3) We discussed how the application should work. | 3) No issues were arised.
Teja Parimi | 1) Shared contact information within the group. | 1) First Group Meeting. | 1) Discussed about team roles. | 1) Discussed about group meeting | 1) Conducted group meeting and discussed questions for the client.
| 2) Initiated first team meeting. | 2) Discussed about group roles. | 2) Discussed about group meeting project. | 2) Discussed about questions for the client. | 2) Client Meeting
| 3) We discussed what actually a campus tour means. | 3) We discussed about the basic requirements for the application | 3) We discussed about the basic requirements for the application | 3) We discussed how the application should work. | 3) No issues were arised.
Rakesh Chitturi | 1) Shared contact information within the group. | 1) First Group Meeting. | 1) Discussed about team roles. | 1) Discussed about group meeting | 1) Conducted group meeting and discussed questions for the client.
| 2) Initiated first team meeting. | 2) Discussed about group roles. | 2) Discussed about group meeting project. | 2) Discussed about questions for the client. | 2) Client Meeting
| 3) We discussed what actually a campus tour means. | 3) We discussed about the basic requirements for the application | 3) We discussed about the basic requirements for the application | 3) We discussed how the application should work. | 3) No issues were arised.
Vamsee Krishna Solasa | 1) Shared contact information within the group. | 1) First Group Meeting. | 1) Discussed about team roles. | 1) Discussed about group meeting | 1) Conducted group meeting and discussed questions for the client.
| 2) Initiated first team meeting. | 2) Discussed about group roles. | 2) Discussed about group meeting project. | 2) Discussed about questions for the client. | 2) Client Meeting
| 3) We discussed what actually a campus tour means. | 3) We discussed about the basic requirements for the application | 3) We discussed about the basic requirements for the application | 3) We discussed how the application should work. | 3) No issues were arised.
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?

## Sep12-Sep16
Daily Stand-up Meeting Report
Week: Sep12-Sep16
Project Name: Campus Cruise
Team Name: Crazy Coders
| Monday | Tuesday | Wednesday | Thursday | Friday
Nayan Reddy Prodduturi | 1) Group Meeting to discuss about requirements. | 1) Group Meeting | 1) Prepared the mockups document and uploaded to the GIT. | 1) Group meeting to add functionalities to the mockups. | 1) Group meeting to discuss questions for the client.
| 2) Analyzing the requirements. | 2) Collected mockup of the user interface. | 2) Group Meeting | 2) Group meeting to discuss questions for the client. | 2) Client meeting
| 3) No issues. | 3) No issue. | 3) No issue. | 3) No issue. | 3) no issue
Mallikharjuna Rao Dande | 1) Group Meeting to discuss about requirements. | 1) Group Meeting | 1) Uploaded files to the GIT | 1) Group meeting to add functionalities to the mockups. | 1) Group meeting to discuss questions for the client.
| 2) Analyzing the requirements. | 2) Prepared mockup of the user interface. | 2) Group Meeting | 2) Group meeting to discuss questions for the client. | 2) Client meeting
| 3) No issue | 3) No issue. | 3) No issue. | 3) No issue. | 3) no issue
Chiranjeevi Sneha Kotu | 1) Group Meeting to discuss about requirements. | 1) Group Meeting | 1) Uploaded files to the GIT | 1) Group meeting to add functionalities to the mockups. | 1) Group meeting to discuss questions for the client.
| 2) Analyzing the requirements. | 2) Designed UI for the UI | 2) Group Meeting | 2) Group meeting to discuss questions for the client. | 2) Client meeting
| 3) No issue | 3) No issue | 3) No issue | 3) No issue. | 3) no issue
Teja Parimi | 1) Group Meeting to discuss about requirements. | 1) Group Meeting | 1) Uploaded files to the GIT | 1) Group meeting to add functionalities to the mockups. | 1) Group meeting to discuss questions for the client.
| 2) Analyzing the requirements. | 2) Tested the quality of the UI | 2) Group Meeting | 2) Group meeting to discuss questions for the client. | 2) Client meeting
| 3) No issue | 3) No issue | 3) No issue | 3) No issue. | 3) no issue
Rakesh Chitturi | 1) Group Meeting to discuss about requirements. | 1) Group Meeting | 1) Uploaded files to the GIT | 1) Group meeting to add functionalities to the mockups. | 1) Group meeting to discuss questions for the client.
| 2) Analyzing the requirements. | 2) Created the use cases for the UI | 2) Group Meeting | 2) Group meeting to discuss questions for the client. | 2) Client meeting
| 3) No issue | 3) No issue | 3) No issue | 3) No issue. | 3) no issue
Vamsee Krishna Solasa | 1) Group Meeting to discuss about requirements. | 1) Group Meeting | 1) Uploaded files to the GIT | 1) Group meeting to add functionalities to the mockups. | 1) Group meeting to discuss questions for the client.
| 2) Analyzing the requirements. | 2) Created the use cases for the UI | 2) Group Meeting | 2) Group meeting to discuss questions for the client. | 2) Client meeting
| 3) No issue | 3) No issue | 3) No issue | 3) No issue. | 3) no issue
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?

## Sep19-Sep23
Daily Stand-up Meeting Report
Week: Sep19-Sep23
Project Name: Campus Cruise
Team Name: Crazy Coders
| Monday | Tuesday | Wednesday | Thursday | Friday
Nayan Reddy Prodduturi | 1) Shared the UI. | 1) Had conversation to decide the application domain | 1) Discussed some use cases to validate the requirements. | 1) Worked on requirement document. | 1) Discussed questions for the client.
| 2) Group meet to make corrections to the UI | 2) Selecting the required tools for the project. | 2) Group meeting | 2) Created GIT repiository and posted files to it | 2) Client meeting
| 3) No issue. | 3) No issue. | 3) No issue | 3) No issue. | 3) No issue.
Mallikharjuna Rao Dande | 1) Shared the UI. | 1) Had conversation to decide the application domain | 1) Discussed some use cases to validate the requirements. | 1) Worked on client managment document. | 1) Discussed questions for the client.
| 2) Group meet to make corrections to the UI | 2) Selecting the required tools for the project. | 2) Group meeting | 2) Posted files to the GIT repository | 2) Client meeting
| 3) No issue. | 3) No issue. | 3) No issue. | 3) No issue. | 3) No issue.
Chiranjeevi Sneha Kotu | 1) Shared the UI. | 1) Had conversation to decide the application domain | 1) Discussed some use cases to validate the requirements. | 1) Worked on requirement document. | 1) Discussed questions for the client.
| 2) Group meet to make corrections to the UI | 2) Selecting the required tools for the project. | 2) Group meeting | 2) Posted files to the GIT repository | 2) Client meeting
| 3) No issue. | 3) No issue. | 3) No issue. | 3) No issue. | 3) No issue.
Teja Parimi | 1) Shared the UI. | 1) Had conversation to decide the application domain | 1) Discussed some use cases to validate the requirements. | 1) Worked on quality managment document. | 1) Discussed questions for the client.
| 2) Group meet to make corrections to the UI | 2) Selecting the required tools for the project. | 2) Group meeting | 2) Posted files to the GIT repository | 2) Client meeting
| 3) No issue. | 3) No issue. | 3) No issue. | 3) No issue. | 3) No issue.
Rakesh Chitturi | 1) Shared the UI. | 1) Had conversation to decide the application domain | 1) Discussed some use cases to validate the requirements. | 1) Worked on testing stratagies. | 1) Discussed questions for the client.
| 2) Group meet to make corrections to the UI | 2) Selecting the required tools for the project. | 2) Group meeting | 2) Posted files to the GIT repository | 2) Client meeting
| 3) No issue. | 3) No issue. | 3) No issue. | 3) No issue. | 3) No issue.
Vamsee Krishna Solasa | 1) Shared the UI. | 1) Had conversation to decide the application domain | 1) Discussed some use cases to validate the requirements. | 1) Worked on issue managment document. | 1) Discussed questions for the client.
| 2) Group meet to make corrections to the UI | 2) Selecting the required tools for the project. | 2) Group meeting | 2) Posted files to the GIT repository | 2) Client meeting
| 3) No issue. | 3) No issue. | 3) No issue. | 3) No issue. | 3) No issue.

## Sept26-Sep30
Daily Stand-up Meeting Report
Week: Sept26-Sep30
Project Name: Campus Cruise
Team Name: Crazy Coders
| Monday | Tuesday | Wednesday | Thursday | Friday
Nayan Reddy Prodduturi | 1) Refined the project documents | 1) Checked use cases. | 1) Updated the requirement document according to the client requirement. | 1) Uploaded the assignment files into the Repository. | 1) Shared the work between the designing and collected the required documents.
| 2) Uploaded files to the GIT | 2) Created mockup screens. | 2) Requirement document Refinement | 2) Scope Documentaion - User Manual | 2) Scope Documentaion - User Manual
| 3) No Issues | 3) No issues | 3) No Issues | 3) No Issues | 3) No Issues
Mallikharjuna Rao Dande | 1) Prepare use case scenarios | 1) Think of new use cases | 1) Create Use cases | 1) Collect Test cases and convert it to use cases | 1) Gather Issues
| 2) Create Usecase templates - Building detection | 2) Create Use cases - Home screen | 2) Create use cases | 2) Scope Document - Use Cases | 2) Scope Document - Use Cases
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Chiranjeevi Sneha Kotu | 1) Work on Requirement document | 1) Requirement discovery - Buildings to be covered | 1) Requirement document - Interface | 1) Requirement Document - Refine interface | 1) Add refined requirements to requirement document to Git hub.
| 2) Requirement Discovery | 2) Requirement Document - Client agreement | 2) Requirement document Refinement | 2) Scope Document - Requirement Documents | 2) Scope Document - Requirement Documents
| 3) No Issues | Need Clients approval | 3) No Issues | 3) No Issues | 3) No Issues
Teja Parimi | 1) Client meeting | 1) Requirement discovery | Verification of requirement document | 1) Designed Moqup for home screen | 2) Designed Scope document - Test Cases
| 2) Aid Requirement discovery | 2) Verification - Requirement Document | 2) Design a Scenario in Moqup | 2) Scope Document - Test Cases | 2) Scope Document - Test Cases
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Rakesh Chitturi | 1) Division of Moqup creation | 1) Moqup flow for home screen | 1) Test Moqup from xiffe.com | 1) Home screen moqup | 1) Added the screen shots to the GIT documents
| 2) Convert a test case to moqup flow | 2) Convert a test case to moqup flow | 2) Design a Scenario in Moqup | 2) Scope Document - Moqup | 2) Scope Document - Moqup
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Vamsee Krishna Solasa | 1) Study and determine issues in requirement documents | 1) Issue discovery - Interface of screens | 1) Issue discovery - Two buildings in a range | 1) Made issue management template | 1) Issue management document created
| 2) Issue Discovery | 2) Issue Discovery | 2) Issue Management Document Template | 2) Scope Document Issue Management | 2) Scope Document Issue Management
| 3) Need additional details on requirement document | 3) Need a template | 3) No Issues | 3) No Issues | 3) No Issues

## Oct02-Oct07
Daily Stand-up Meeting Report
Week: Oct/02-Oct/07
Project Name: Campus Cruise
Team Name: Crazy Coders
| Monday | Tuesday | Wednesday | Thursday | Friday
Nayan Reddy Prodduturi | 1) Work division - User manual | 1) Created template | 1) Took Scenarios and convert them to use manual scenarios | 1) Created user manual | 1) User manual refinement
| 2) Create Template for user manual | 2) Studied the requirement document to get an understanding of places where user situation need instructions | 2) Create user manual | 2) Verify all test cases are made to instructions | 2) Refined the user manual and submitted it to GIT
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Mallikharjuna Rao Dande | 1) Made scope documents | 1) Make use case diagrams for approaching building scenario | 1) Make use case diagrams for the home screen | 1) Discuss on the how to make the map be aware buildings range | 1) Discussed on the mechanic of app
| 2) Make use case diagrams for approaching building scenario | 2) Make use case diagrams for the home screen | 2) Make use case diagrams fro QR code Scan | 2) Check on the mechanic of the application | 2) Gather the lattitude and Longitude of the campus buildings
| 3) no issues | 3) no issues | 3) no issues | 3) Need reliable source for gathering he source of the map data | 3) No issues
Chiranjeevi Sneha Kotu | 1) Discussed on the home screen | 2) Created backgroud to use for moqup | 1) Createed moqup | 1) Verifeid Use case diagrams | 1) Requirement management document
| 2) Created backgroud to use for moqup | 2) Collaborated with team to create a moqup for different screens | 2) Verifed hte use case diagram | 2) Verifeid hte requirement management document | 2) verified the issues management document
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Teja Parimi | 1) Scope document - Test case document | 1) Android tutorial | 1) Created test case - distance between buildings | 1) Test case - Data connection lost | 1) Test case - Approaching a document
| 2) Did android tutorial | 2) Created test case - Distance between buildings | 2) Created a test case - Data connection lost | 2) Created test cases - Appraoching a building | 2) Verifed the test case document
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Rakesh Chitturi | 1) Scope document - Moqup | 1) Moqup - You are here screen | 1) Verification of moqup | 1) Moqup - Home screen | 1) Moqup - Verification
| 2) Created moqup for you are here screen | 2) Verified the moqup | 2) Created the moqup - home screen in tablet background | 2) Verified the moqup | 2) Uploaded the moqup to GIT
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Vamsee Krishna Solasa | 1) Scope Document Issue Management | 1) Test case document - Verification | 1) Testcase document - verification | 1) Use case diagram - helped | 1) requirement document creation - help
| 2) Veried the moqup | 2) Verified the test case document | 2) Helped with Use case diagram | 2) Helped with the requirement document creation | 2) Verified and uploaded the Issues managemetn file to GIT
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?

## Oct10 - Oct14
Daily Stand-up Meeting Report
Week: Oct10-Oct14
Project Name: Campus Cruise
Team Name: Crazy Coders
| Monday | Tuesday | Wednesday | Thursday | Friday
Nayan Reddy Prodduturi | 1) Working on User manual | 1) Creation of template | 1) Taking Scenarios and convert them to use manual scenarios | 1) Created user manual | 1) User manual refinement
| 2) Create Template for user manual | 2) Studied the requirement document to get an understanding of places where user situation need instructions | 2) Create user manual | 2) Verify all test cases are made to instructions | 2) Refined the user manual and submitted it to GIT
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Mallikharjuna Rao Dande | 1) | 1) | 1) | 1) | 1)
| 2) | 2) | 2) | 2) | 2)
| 3) no issues | 3) no issues | 3) no issues | 3) Need reliable source for gathering he source of the map data | 3) No issues
Chiranjeevi Sneha Kotu | 1) Worked on home screen | 1) Created backgroud to use for moqup | 1) Created moqup | 1) Verified use case diagrams | 1) Requirement management document uploaded to GIT
| 2) Created moqups for the home screen | 2) Collaborated with team to create a moqup for different screens | 2) Verifed the use case diagram | 2) Verifeid the requirement management document | 2) verified the requirement document
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Teja Parimi | 1) Scope document - Test case document | 1) Android tutorial | 1) Created test case - distance between buildings | 1) Test case - Data connection lost | 1) Test case - Approaching a document
| 2) Did android tutorial | 2) Created test case - Distance between buildings | 2) Created a test case - Data connection lost | 2) Created test cases - Appraoching a building | 2) Verifed the test case document
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Rakesh Chitturi | 1) Scope document - Moqup | 1) working on mockups of home screen | 1) Verification of all mockups | 1) Moqup - Home screen | 1) Moqup - Verification
| 2) Created moqup for you are here screen | 2) Verified the moqup | 2) Created the moqup - home screen in tablet background | 2) Verified the moqup | 2) Uploaded the moqup to GIT
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Vamsee Krishna Solasa | 1) Scope Document Issue Management | 1) Test case document - Verification | 1) Testcase document - verification | 1) Use case diagram - helped | 1) requirement document creation - help
| 2) Veried the moqup | 2) Verified the test case document | 2) Helped with Use case diagram | 2) Helped with the requirement document creation | 2) Verified and uploaded the Issues managemetn file to GIT
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?

## Oct17-Oct21
Daily Stand-up Meeting Report
Week: Oct17-Oct21
Project Name: Campus Cruise
Team Name: Crazy Coders
| Monday | Tuesday | Wednesday | Thursday | Friday
Nayan Reddy Prodduturi | 1) Added tour guide to the user manual. | 1) Created template | 1) Work on User manul | 1) Verifing the document | 1) Worked on Installation guide
| 2) collection of Requirements from client | 2) Collaborated with team to discuss the work done till now | 2) Create user manual | 2) verification of the document and tours | 2) Refined the user manual and submitted it to GIT
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Mallikharjuna Rao Dande
| 3) no issues | 3) no issues | 3) no issues | 3) Need reliable source for gathering he source of the map data | 3) No issues
Chiranjeevi Sneha Kotu | 1) working on SRS document | 1) working on requiremnts document | 1) working on the RD | 1) Verifing the document | 1) Requirement management document
| 2) collection of Requirements from client | 2) Collaborated with team to discuss the work done till now | 2) verification and checking the documents | 2) verification and checking the documents | 2) verified the Requirement management document
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Teja Parimi | 1) Scope document - Test case document | 1) Android tutorial | 1) Created test case - distance between buildings | 1) Test case - Data connection lost | 1) Test case - Approaching a document
| 2) Did android tutorial | 2) Created test case - Distance between buildings | 2) Created a test case - Data connection lost | 2) Created test cases - Appraoching a building | 2) Verifed the test case document
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Rakesh Chitturi | 1) Scope document - Moqup | 1) Moqup - You are here screen | 1) Verification of moqup | 1) Moqup - Home screen | 1) Moqup - Verification
| 2) Created moqup for you are here screen | 2) Verified the moqup | 2) Created the moqup - home screen in tablet background | 2) Verified the moqup | 2) Uploaded the moqup to GIT
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Vamsee Krishna Solasa | 1) Scope Document Issue Management | 1) Test case document - Verification | 1) Testcase document - verification | 1) Use case diagram - helped | 1) requirement document creation - help
| 2) Veried the moqup | 2) Verified the test case document | 2) Helped with Use case diagram | 2) Helped with the requirement document creation | 2) Verified and uploaded the Issues managemetn file to GIT
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?

## Oct 24-Oct28
Daily Stand-up Meeting Report
Week: Oct24-Oct28
Project Name: Campus Cruise
Team Name: Crazy Coders
| Monday | Tuesday | Wednesday | Thursday | Friday
Nayan Reddy Prodduturi | 1) Work division - Installation maual | 1) Working on the client given new requirements | 1) Added new tour guide to user manual. | 1) Work division - Scope management | 1) Backup for a team member who is unavailable.
| 2) Create Template for installation manual | 2) Completing the installation guide. | 2) Update installation manual | 2) Updated the scope management plan. | 2) Refined the scope management plan.
| 3) No Issues | 3) No Issues | 3) No Issues | 3) Team menmber un-available. | 3) No Issues
Mallikharjuna Rao Dande
| 3) no issues | 3) no issues | 3) no issues | 3) Need reliable source for gathering he source of the map data | 3) No issues
Chiranjeevi Sneha Kotu | 1) Working on the client given new requirements | 1) Working on the client given new requirements | 1) Working on the client given new requirements | 1) Working on the client given new requirements | 1) Working on the client given new requirements
| 2) completing the requirement documents | 2) completing the requirement documents | 2) completing the requirement documents | 2) completing the requirement documents | 2) completing the requirement documents
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Teja Parimi | 1) Scope document - Test case document | 1) Android tutorial | 1) Created test case - distance between buildings | 1) Test case - Data connection lost | 1) Test case - Approaching a document
| 2) Did android tutorial | 2) Created test case - Distance between buildings | 2) Created a test case - Data connection lost | 2) Created test cases - Appraoching a building | 2) Verifed the test case document
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Rakesh Chitturi | 1) Scope document - Moqup | 1) Moqup - You are here screen | 1) Verification of moqup | 1) Moqup - Home screen | 1) Moqup - Verification
| 2) Created moqup for you are here screen | 2) Verified the moqup | 2) Created the moqup - home screen in tablet background | 2) Verified the moqup | 2) Uploaded the moqup to GIT
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Vamsee Krishna Solasa | 1) Scope Document Issue Management | 1) Test case document - Verification | 1) Testcase document - verification | 1) Use case diagram - helped | 1) requirement document creation - help
| 2) Veried the moqup | 2) Verified the test case document | 2) Helped with Use case diagram | 2) Helped with the requirement document creation | 2) Verified and uploaded the Issues managemetn file to GIT
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?

## Oct31-Nov4
Daily Stand-up Meeting Report
Week: Oct31-Nov4
Project Name: Campus Cruise
Team Name: Crazy Coders
| Monday | Tuesday | Wednesday | Thursday | Friday
Nayan Reddy Prodduturi | 1) Discussed on the home screen | 1) Created template | 1) Took Scenarios and convert them to use manual scenarios | 1) Created user manual | 1) User manual refinement
| 2) Learned android tutorial. | 2) Learned android tutorial. | 2) Edited the installation guide. | 2) Learned android tutorial. | 2) Learned android tutorial.
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Mallikharjuna Rao Dande
| 3) no issues | 3) no issues | 3) no issues | 3) Need reliable source for gathering he source of the map data | 3) No issues
Chiranjeevi Sneha Kotu | 1) Discussed on the home screen | 1) Created backgroud to use for moqup | 1) Createed moqup | 1) Verifeid Use case diagrams | 1) Requirement management document
| 2) Created backgroud to use for moqup | 2) Collaborated with team to create a moqup for different screens | 2) Verifed hte use case diagram | 2) Verifeid hte requirement management document | 2) verified the issues management document
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Teja Parimi | 1) Scope document - Test case document | 1) Android tutorial | 1) Created test case - distance between buildings | 1) Test case - Data connection lost | 1) Test case - Approaching a document
| 2) Did android tutorial | 2) Created test case - Distance between buildings | 2) Created a test case - Data connection lost | 2) Created test cases - Appraoching a building | 2) Verifed the test case document
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Rakesh Chitturi | 1) Scope document - Moqup | 1) Moqup - You are here screen | 1) Verification of moqup | 1) Moqup - Home screen | 1) Moqup - Verification
| 2) Created moqup for you are here screen | 2) Verified the moqup | 2) Created the moqup - home screen in tablet background | 2) Verified the moqup | 2) Uploaded the moqup to GIT
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Vamsee Krishna Solasa | 1) Scope Document Issue Management | 1) Test case document - Verification | 1) Testcase document - verification | 1) Use case diagram - helped | 1) requirement document creation - help
| 2) Veried the moqup | 2) Verified the test case document | 2) Helped with Use case diagram | 2) Helped with the requirement document creation | 2) Verified and uploaded the Issues managemetn file to GIT
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?

## Nov7-Nov11
Daily Stand-up Meeting Report
Week: Nov7-Nov11
Project Name: Campus Cruise
Team Name: Crazy Coders
| Monday | Tuesday | Wednesday | Thursday | Friday
Nayan Reddy Prodduturi | 1) Preparing and working on all the documents of end term presentation. | 1) Preparing and working on all the documents of end term presentation. | 1) Preparing and working on all the documents of end term presentation. | 1) Preparing and working on all the documents of end term presentation. | 1) Preparing and working on all the documents of end term presentation.
| 2) Working with group and getting all the documents ready and uploading on git hub and working collaboratively checking all the works | 2) Working with group and getting all the documents ready and uploading on git hub and working collaboratively checking all the works | 2) Working with group and getting all the documents ready and uploading on git hub and working collaboratively checking all the works | 2) Working with group and getting all the documents ready and uploading on git hub and working collaboratively checking all the works | 2) Working with group and getting all the documents ready and uploading on git hub and working collaboratively checking all the works
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Mallikharjuna Rao Dande
| 3) no issues | 3) no issues | 3) no issues | 3) Need reliable source for gathering he source of the map data | 3) No issues
Chiranjeevi Sneha Kotu | 1) Preparing and working on all the requirments for the end term presentation | 1) Preparing and working on all the requirments for the end term presentation | 1) Preparing and working on all the requirments for the end term presentation | 1) Preparing and working on all the requirments for the end term presentation | 1) Preparing and working on all the requirments for the end term presentation
| 2) Working with group and getting all the documents ready and uploading on git hub and working collaboratively checking all the works | 2) Working with group and getting all the documents ready and uploading on git hub and working collaboratively checking all the works | 2) Working with group and getting all the documents ready and uploading on git hub and working collaboratively checking all the works | 2) Working with group and getting all the documents ready and uploading on git hub and working collaboratively checking all the works | 2) Working with group and getting all the documents ready and uploading on git hub and working collaboratively checking all the works
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Teja Parimi | 1) Scope document - Test case document | 1) Android tutorial | 1) Created test case - distance between buildings | 1) Test case - Data connection lost | 1) Test case - Approaching a document
| 2) Did android tutorial | 2) Created test case - Distance between buildings | 2) Created a test case - Data connection lost | 2) Created test cases - Appraoching a building | 2) Verifed the test case document
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Rakesh Chitturi | 1) Scope document - Moqup | 1) Moqup - You are here screen | 1) Verification of moqup | 1) Moqup - Home screen | 1) Moqup - Verification
| 2) Created moqup for you are here screen | 2) Verified the moqup | 2) Created the moqup - home screen in tablet background | 2) Verified the moqup | 2) Uploaded the moqup to GIT
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Vamsee Krishna Solasa | 1) Scope Document Issue Management | 1) Test case document - Verification | 1) Testcase document - verification | 1) Use case diagram - helped | 1) requirement document creation - help
| 2) Veried the moqup | 2) Verified the test case document | 2) Helped with Use case diagram | 2) Helped with the requirement document creation | 2) Verified and uploaded the Issues managemetn file to GIT
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?

## Nov14-Nov18
Daily Stand-up Meeting Report
Week: Nov14-Nov18
Project Name: Campus Cruise
Team Name: Crazy Coders
| Monday | Tuesday | Wednesday | Thursday | Friday
Nayan Reddy Prodduturi
Mallikharjuna Rao Dande
Chiranjeevi Sneha Kotu
Teja Parimi
Rakesh Chitturi
Vamsee Krishna Solasa
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?