## Sep05-Sep09
Daily Stand-up Meeting Report
Week: Sep05-Sep09
Project Name: Campus Cruise
Team Name: Crazy Coders
| Monday | Tuesday | Wednesday | Thursday | Friday
Nayan Reddy Prodduturi | 1) Shared contact information within the group. | 1) First Group Meeting. | 1) Discussed about team roles. | 1) Discussed about group meeting | 1) Conducted group meeting and discussed questions for the client.
| 2) Initiated first team meeting. | 2) Discussed about group roles. | 2) Discussed about group meeting project. | 2) Discussed about questions for the client. | 2) Client Meeting
| 3) We discussed what actually a campus tour means. | 3) We discussed about the basic requirements for the application | 3) We discussed about the basic requirements for the application | 3) We discussed how the application should work. | 3) No issues were arised.
Mallikharjuna Rao Dande | 1) Shared contact information within the group. | 1) First Group Meeting. | 1) Discussed about team roles. | 1) Discussed about group meeting | 1) Conducted group meeting and discussed questions for the client.
| 2) Initiated first team meeting. | 2) Discussed about group roles. | 2) Discussed about group meeting project. | 2) Discussed about questions for the client. | 2) Client Meeting
| 3) We discussed what actually a campus tour means. | 3) We discussed about the basic requirements for the application | 3) We discussed about the basic requirements for the application | 3) We discussed how the application should work. | 3) No issues were arised.
Chiranjeevi Sneha Kotu | 1) Shared contact information within the group. | 1) First Group Meeting. | 1) Discussed about team roles. | 1) Discussed about group meeting | 1) Conducted group meeting and discussed questions for the client.
| 2) Initiated first team meeting. | 2) Discussed about group roles. | 2) Discussed about group meeting project. | 2) Discussed about questions for the client. | 2) Client Meeting
| 3) We discussed what actually a campus tour means. | 3) We discussed about the basic requirements for the application | 3) We discussed about the basic requirements for the application | 3) We discussed how the application should work. | 3) No issues were arised.
Teja Parimi | 1) Shared contact information within the group. | 1) First Group Meeting. | 1) Discussed about team roles. | 1) Discussed about group meeting | 1) Conducted group meeting and discussed questions for the client.
| 2) Initiated first team meeting. | 2) Discussed about group roles. | 2) Discussed about group meeting project. | 2) Discussed about questions for the client. | 2) Client Meeting
| 3) We discussed what actually a campus tour means. | 3) We discussed about the basic requirements for the application | 3) We discussed about the basic requirements for the application | 3) We discussed how the application should work. | 3) No issues were arised.
Rakesh Chitturi | 1) Shared contact information within the group. | 1) First Group Meeting. | 1) Discussed about team roles. | 1) Discussed about group meeting | 1) Conducted group meeting and discussed questions for the client.
| 2) Initiated first team meeting. | 2) Discussed about group roles. | 2) Discussed about group meeting project. | 2) Discussed about questions for the client. | 2) Client Meeting
| 3) We discussed what actually a campus tour means. | 3) We discussed about the basic requirements for the application | 3) We discussed about the basic requirements for the application | 3) We discussed how the application should work. | 3) No issues were arised.
Vamsee Krishna Solasa | 1) Shared contact information within the group. | 1) First Group Meeting. | 1) Discussed about team roles. | 1) Discussed about group meeting | 1) Conducted group meeting and discussed questions for the client.
| 2) Initiated first team meeting. | 2) Discussed about group roles. | 2) Discussed about group meeting project. | 2) Discussed about questions for the client. | 2) Client Meeting
| 3) We discussed what actually a campus tour means. | 3) We discussed about the basic requirements for the application | 3) We discussed about the basic requirements for the application | 3) We discussed how the application should work. | 3) No issues were arised.
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?

## Sep12-Sep16
Daily Stand-up Meeting Report
Week: Sep12-Sep16
Project Name: Campus Cruise
Team Name: Crazy Coders
| Monday | Tuesday | Wednesday | Thursday | Friday
Nayan Reddy Prodduturi | 1) Group Meeting to discuss about requirements. | 1) Group Meeting | 1) Prepared the mockups document and uploaded to the GIT. | 1) Group meeting to add functionalities to the mockups. | 1) Group meeting to discuss questions for the client.
| 2) Analyzing the requirements. | 2) Collected mockup of the user interface. | 2) Group Meeting | 2) Group meeting to discuss questions for the client. | 2) Client meeting
| 3) No issues. | 3) No issue. | 3) No issue. | 3) No issue. | 3) no issue
Mallikharjuna Rao Dande | 1) Group Meeting to discuss about requirements. | 1) Group Meeting | 1) Uploaded files to the GIT | 1) Group meeting to add functionalities to the mockups. | 1) Group meeting to discuss questions for the client.
| 2) Analyzing the requirements. | 2) Prepared mockup of the user interface. | 2) Group Meeting | 2) Group meeting to discuss questions for the client. | 2) Client meeting
| 3) No issue | 3) No issue. | 3) No issue. | 3) No issue. | 3) no issue
Chiranjeevi Sneha Kotu | 1) Group Meeting to discuss about requirements. | 1) Group Meeting | 1) Uploaded files to the GIT | 1) Group meeting to add functionalities to the mockups. | 1) Group meeting to discuss questions for the client.
| 2) Analyzing the requirements. | 2) Designed UI for the UI | 2) Group Meeting | 2) Group meeting to discuss questions for the client. | 2) Client meeting
| 3) No issue | 3) No issue | 3) No issue | 3) No issue. | 3) no issue
Teja Parimi | 1) Group Meeting to discuss about requirements. | 1) Group Meeting | 1) Uploaded files to the GIT | 1) Group meeting to add functionalities to the mockups. | 1) Group meeting to discuss questions for the client.
| 2) Analyzing the requirements. | 2) Tested the quality of the UI | 2) Group Meeting | 2) Group meeting to discuss questions for the client. | 2) Client meeting
| 3) No issue | 3) No issue | 3) No issue | 3) No issue. | 3) no issue
Rakesh Chitturi | 1) Group Meeting to discuss about requirements. | 1) Group Meeting | 1) Uploaded files to the GIT | 1) Group meeting to add functionalities to the mockups. | 1) Group meeting to discuss questions for the client.
| 2) Analyzing the requirements. | 2) Created the use cases for the UI | 2) Group Meeting | 2) Group meeting to discuss questions for the client. | 2) Client meeting
| 3) No issue | 3) No issue | 3) No issue | 3) No issue. | 3) no issue
Vamsee Krishna Solasa | 1) Group Meeting to discuss about requirements. | 1) Group Meeting | 1) Uploaded files to the GIT | 1) Group meeting to add functionalities to the mockups. | 1) Group meeting to discuss questions for the client.
| 2) Analyzing the requirements. | 2) Created the use cases for the UI | 2) Group Meeting | 2) Group meeting to discuss questions for the client. | 2) Client meeting
| 3) No issue | 3) No issue | 3) No issue | 3) No issue. | 3) no issue
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?

## Sep19-Sep23
Daily Stand-up Meeting Report
Week: Sep19-Sep23
Project Name: Campus Cruise
Team Name: Crazy Coders
| Monday | Tuesday | Wednesday | Thursday | Friday
Nayan Reddy Prodduturi | 1) Shared the UI. | 1) Had conversation to decide the application domain | 1) Discussed some use cases to validate the requirements. | 1) Worked on requirement document. | 1) Discussed questions for the client.
| 2) Group meet to make corrections to the UI | 2) Selecting the required tools for the project. | 2) Group meeting | 2) Created GIT repiository and posted files to it | 2) Client meeting
| 3) No issue. | 3) No issue. | 3) No issue | 3) No issue. | 3) No issue.
Mallikharjuna Rao Dande | 1) Shared the UI. | 1) Had conversation to decide the application domain | 1) Discussed some use cases to validate the requirements. | 1) Worked on client managment document. | 1) Discussed questions for the client.
| 2) Group meet to make corrections to the UI | 2) Selecting the required tools for the project. | 2) Group meeting | 2) Posted files to the GIT repository | 2) Client meeting
| 3) No issue. | 3) No issue. | 3) No issue. | 3) No issue. | 3) No issue.
Chiranjeevi Sneha Kotu | 1) Shared the UI. | 1) Had conversation to decide the application domain | 1) Discussed some use cases to validate the requirements. | 1) Worked on requirement document. | 1) Discussed questions for the client.
| 2) Group meet to make corrections to the UI | 2) Selecting the required tools for the project. | 2) Group meeting | 2) Posted files to the GIT repository | 2) Client meeting
| 3) No issue. | 3) No issue. | 3) No issue. | 3) No issue. | 3) No issue.
Teja Parimi | 1) Shared the UI. | 1) Had conversation to decide the application domain | 1) Discussed some use cases to validate the requirements. | 1) Worked on quality managment document. | 1) Discussed questions for the client.
| 2) Group meet to make corrections to the UI | 2) Selecting the required tools for the project. | 2) Group meeting | 2) Posted files to the GIT repository | 2) Client meeting
| 3) No issue. | 3) No issue. | 3) No issue. | 3) No issue. | 3) No issue.
Rakesh Chitturi | 1) Shared the UI. | 1) Had conversation to decide the application domain | 1) Discussed some use cases to validate the requirements. | 1) Worked on testing stratagies. | 1) Discussed questions for the client.
| 2) Group meet to make corrections to the UI | 2) Selecting the required tools for the project. | 2) Group meeting | 2) Posted files to the GIT repository | 2) Client meeting
| 3) No issue. | 3) No issue. | 3) No issue. | 3) No issue. | 3) No issue.
Vamsee Krishna Solasa | 1) Shared the UI. | 1) Had conversation to decide the application domain | 1) Discussed some use cases to validate the requirements. | 1) Worked on issue managment document. | 1) Discussed questions for the client.
| 2) Group meet to make corrections to the UI | 2) Selecting the required tools for the project. | 2) Group meeting | 2) Posted files to the GIT repository | 2) Client meeting
| 3) No issue. | 3) No issue. | 3) No issue. | 3) No issue. | 3) No issue.

## Sept26-Sep30
Daily Stand-up Meeting Report
Week: Sept26-Sep30
Project Name: Campus Cruise
Team Name: Crazy Coders
| Monday | Tuesday | Wednesday | Thursday | Friday
Nayan Reddy Prodduturi | 1) Refined the project documents | 1) Checked use cases. | 1) Updated the requirement document according to the client requirement. | 1) Uploaded the assignment files into the Repository. | 1) Shared the work between the designing and collected the required documents.
| 2) Uploaded files to the GIT | 2) Created mockup screens. | 2) Requirement document Refinement | 2) Scope Documentaion - User Manual | 2) Scope Documentaion - User Manual
| 3) No Issues | 3) No issues | 3) No Issues | 3) No Issues | 3) No Issues
Mallikharjuna Rao Dande | 1) Prepare use case scenarios | 1) Think of new use cases | 1) Create Use cases | 1) Collect Test cases and convert it to use cases | 1) Gather Issues
| 2) Create Usecase templates - Building detection | 2) Create Use cases - Home screen | 2) Create use cases | 2) Scope Document - Use Cases | 2) Scope Document - Use Cases
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Chiranjeevi Sneha Kotu | 1) Work on Requirement document | 1) Requirement discovery - Buildings to be covered | 1) Requirement document - Interface | 1) Requirement Document - Refine interface | 1) Add refined requirements to requirement document to Git hub.
| 2) Requirement Discovery | 2) Requirement Document - Client agreement | 2) Requirement document Refinement | 2) Scope Document - Requirement Documents | 2) Scope Document - Requirement Documents
| 3) No Issues | Need Clients approval | 3) No Issues | 3) No Issues | 3) No Issues
Teja Parimi | 1) Client meeting | 1) Requirement discovery | Verification of requirement document | 1) Designed Moqup for home screen | 2) Designed Scope document - Test Cases
| 2) Aid Requirement discovery | 2) Verification - Requirement Document | 2) Design a Scenario in Moqup | 2) Scope Document - Test Cases | 2) Scope Document - Test Cases
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Rakesh Chitturi | 1) Division of Moqup creation | 1) Moqup flow for home screen | 1) Test Moqup from xiffe.com | 1) Home screen moqup | 1) Added the screen shots to the GIT documents
| 2) Convert a test case to moqup flow | 2) Convert a test case to moqup flow | 2) Design a Scenario in Moqup | 2) Scope Document - Moqup | 2) Scope Document - Moqup
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Vamsee Krishna Solasa | 1) Study and determine issues in requirement documents | 1) Issue discovery - Interface of screens | 1) Issue discovery - Two buildings in a range | 1) Made issue management template | 1) Issue management document created
| 2) Issue Discovery | 2) Issue Discovery | 2) Issue Management Document Template | 2) Scope Document Issue Management | 2) Scope Document Issue Management
| 3) Need additional details on requirement document | 3) Need a template | 3) No Issues | 3) No Issues | 3) No Issues

## Oct02-Oct07
Daily Stand-up Meeting Report
Week: Oct/02-Oct/07
Project Name: Campus Cruise
Team Name: Crazy Coders
| Monday | Tuesday | Wednesday | Thursday | Friday
Nayan Reddy Prodduturi | 1) Work division - User manual | 1) Created template | 1) Took Scenarios and convert them to use manual scenarios | 1) Created user manual | 1) User manual refinement
| 2) Create Template for user manual | 2) Studied the requirement document to get an understanding of places where user situation need instructions | 2) Create user manual | 2) Verify all test cases are made to instructions | 2) Refined the user manual and submitted it to GIT
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Mallikharjuna Rao Dande | 1) Made scope documents | 1) Make use case diagrams for approaching building scenario | 1) Make use case diagrams for the home screen | 1) Discuss on the how to make the map be aware buildings range | 1) Discussed on the mechanic of app
| 2) Make use case diagrams for approaching building scenario | 2) Make use case diagrams for the home screen | 2) Make use case diagrams fro QR code Scan | 2) Check on the mechanic of the application | 2) Gather the lattitude and Longitude of the campus buildings
| 3) no issues | 3) no issues | 3) no issues | 3) No issues | 3) No issues
Chiranjeevi Sneha Kotu | 1) Discussed on the home screen | 2) Created backgroud to use for moqup | 1) Createed moqup | 1) Verifeid Use case diagrams | 1) Requirement management document
| 2) Created backgroud to use for moqup | 2) Collaborated with team to create a moqup for different screens | 2) Verifed hte use case diagram | 2) Verifeid hte requirement management document | 2) verified the issues management document
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Teja Parimi | 1) Scope document - Test case document | 1) Android tutorial | 1) Created test case - distance between buildings | 1) Test case - Data connection lost | 1) Test case - Approaching a document
| 2) Did android tutorial | 2) Created test case - Distance between buildings | 2) Created a test case - Data connection lost | 2) Created test cases - Appraoching a building | 2) Verifed the test case document
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Rakesh Chitturi | 1) Scope document - Moqup | 1) Moqup - You are here screen | 1) Verification of moqup | 1) Moqup - Home screen | 1) Moqup - Verification
| 2) Created moqup for you are here screen | 2) Verified the moqup | 2) Created the moqup - home screen in tablet background | 2) Verified the moqup | 2) Uploaded the moqup to GIT
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Vamsee Krishna Solasa | 1) Scope Document Issue Management | 1) Test case document - Verification | 1) Testcase document - verification | 1) Use case diagram - helped | 1) requirement document creation - help
| 2) Veried the moqup | 2) Verified the test case document | 2) Helped with Use case diagram | 2) Helped with the requirement document creation | 2) Verified and uploaded the Issues managemetn file to GIT
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?

## Oct10 - Oct14
Daily Stand-up Meeting Report
Week: Oct10-Oct14
Project Name: Campus Cruise
Team Name: Crazy Coders
| Monday | Tuesday | Wednesday | Thursday | Friday
Nayan Reddy Prodduturi | 1) Working on User manual | 1) Creation of template | 1) Taking Scenarios and convert them to use manual scenarios | 1) Created user manual | 1) User manual refinement
| 2) Create Template for user manual | 2) Studied the requirement document to get an understanding of places where user situation need instructions | 2) Create user manual | 2) Verify all test cases are made to instructions | 2) Refined the user manual and submitted it to GIT
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Mallikharjuna Rao Dande | 1)Delve into the requirement document and discover additional requirements. | 1) Found a requirement and worked on its use case ( Error flow of two buildings senario) | 1) Met with client and found additional requirement i.e Make the App generic for all campuses | 1) Discussed and created a use case diagram for generic campus tour app | 1) Requirement discovery for virtual tour
| 2) Worked on Requiremetns from previous milestone to asses any missed requirements | 2)Meet with client once and discuss on the progress. | 2)Discuss on additional things to add for the existing requirements. | 2)Work on any other issues from previous weeks. | 2) Use case diagrams for campus tour
| 3) no issues | 3) no issues | 3) no issues | 3) No issues | 3) No issues
Chiranjeevi Sneha Kotu | 1) Worked on home screen | 1) Created backgroud to use for moqup | 1) Created moqup | 1) Verified use case diagrams | 1) Requirement management document uploaded to GIT
| 2) Created moqups for the home screen | 2) Collaborated with team to create a moqup for different screens | 2) Verifed the use case diagram | 2) Verifeid the requirement management document | 2) verified the requirement document
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Teja Parimi | 1) Scope document - Test case document | 1) Android tutorial | 1) Created test case - distance between buildings | 1) Test case - Data connection lost | 1) Test case - Approaching a document
| 2) Did android tutorial | 2) Created test case - Distance between buildings | 2) Created a test case - Data connection lost | 2) Created test cases - Appraoching a building | 2) Verifed the test case document
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Rakesh Chitturi | 1) Scope document - Moqup | 1) working on mockups of home screen | 1) Verification of all mockups | 1) Moqup - Home screen | 1) Moqup - Verification
| 2) Created moqup for you are here screen | 2) Verified the moqup | 2) Created the moqup - home screen in tablet background | 2) Verified the moqup | 2) Uploaded the moqup to GIT
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Vamsee Krishna Solasa | 1) Added two scenarios for use cases | 1) Worked on the probable issues | 1) Worked on the requirements document | 1) Added few requirements after the client meeting | 1) Verified the requirement document
| 2) Verified the moqups created | 2) Resolved the issues | 2) Helped with Use case diagram | 2) updated the requirement document | 2) Verified the moqups created
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?

## Oct17-Oct21
Daily Stand-up Meeting Report
Week: Oct17-Oct21
Project Name: Campus Cruise
Team Name: Crazy Coders
| Monday | Tuesday | Wednesday | Thursday | Friday
Nayan Reddy Prodduturi | 1) Added tour guide to the user manual. | 1) Created template | 1) Work on User manul | 1) Verifing the document | 1) Worked on Installation guide
| 2) collection of Requirements from client | 2) Collaborated with team to discuss the work done till now | 2) Create user manual | 2) verification of the document and tours | 2) Refined the user manual and submitted it to GIT
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Mallikharjuna Rao Dande | 1) Use case diagrams for campus tour | 1) divided the project management plan | 1) worked on change management document | 1) worked on change management document | 1) worked on Stakeholder management plan
| 2) Created use case diagram for offline campus tour | 2) started working on project management plan | 2) worked on communications management plan | 2) helped to work on issues management plan | 2) completed stakeholder management plan
| 3) no issues | 3) no issues | 3) no issues | 3) No issues | 3) No issues
Chiranjeevi Sneha Kotu | 1) working on SRS document | 1) working on requiremnts document | 1) working on the RD | 1) Verifing the document | 1) Requirement management document
| 2) collection of Requirements from client | 2) Collaborated with team to discuss the work done till now | 2) verification and checking the documents | 2) verification and checking the documents | 2) verified the Requirement management document
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Teja Parimi | 1) did small sample projects on Android | 1) Supervised the use cases | 1) Created a test case | 1) worked on voice command test case | 1) Tested the Use Case Document
| 2)working of lacking knowledge on android | 2) Created test case - Distance between buildings | 2) Created a test case - Data connection lost | 2) Created test cases - Appraoching a building | 2) Verifed the test case document
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Rakesh Chitturi | 1) Scope document - Moqup | 1) Moqup - You are here screen | 1) Verification of moqup | 1) Moqup - Home screen | 1) Moqup - Verification
| 2) Created moqup for you are here screen | 2) Verified the moqup | 2) Created the moqup - home screen in tablet background | 2) Verified the moqup | 2) Uploaded the moqup to GIT
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Vamsee Krishna Solasa | 1) Getting started with the android | 1) Created an use case scenario | 1) Verified the moqup- home created | 1) verified the test case- Approaching a building | 1)Helped in moqup and use case creations
| 2)online tutorials about android | 2) worked on the requirements document to make sure that the team didn’t miss anything for the week | 2) Helped with Use case diagram | 2) verified the moqup- for you are here screen | 2) Verified and uploaded the Issues managemetn file to GIT
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?

## Oct 24-Oct28
Daily Stand-up Meeting Report
Week: Oct24-Oct28
Project Name: Campus Cruise
Team Name: Crazy Coders
| Monday | Tuesday | Wednesday | Thursday | Friday
Nayan Reddy Prodduturi | 1) Work division - Installation maual | 1) Working on the client given new requirements | 1) Added new tour guide to user manual. | 1) Work division - Scope management | 1) Backup for a team member who is unavailable.
| 2) Create Template for installation manual | 2) Completing the installation guide. | 2) Update installation manual | 2) Updated the scope management plan. | 2) Refined the scope management plan.
| 3) No Issues | 3) No Issues | 3) No Issues | 3) Team menmber un-available. | 3) No Issues
Mallikharjuna Rao Dande | 1) worked on issues management plan | 1) worked on Acceptance plan | 1) completed change management plan | 1) competed stakeholder management plan | 1) delegated acceptance plan to Rakesh chitturi
| 2) worked on acceptance plan | 2) worked on change management document | 2) Met with client to discuss the progress | 2) requirement discovery for virtual tour | 2) virtual tour use case diagram
| 3) no issues | 3) no issues | 3) no issues | 3) no issues | 3) No issues
Chiranjeevi Sneha Kotu | 1) Working on the client given new requirements | 1) Working on the client given new requirements | 1) Working on the client given new requirements | 1) Working on the client given new requirements | 1) Working on the client given new requirements
| 2) completing the requirement documents | 2) completing the requirement documents | 2) completing the requirement documents | 2) completing the requirement documents | 2) completing the requirement documents
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Teja Parimi | 1) Scope document - Test case document | 1) Android tutorial | 1) Created test case - distance between buildings | 1) Test case - Data connection lost | 1) Test case - Approaching a document
| 2) Did android tutorial | 2) Created test case - Distance between buildings | 2) Created a test case - Data connection lost | 2) Created test cases - Appraoching a building | 2) Verifed the test case document
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Rakesh Chitturi | 1) Mockups screens | 1) Moqup - You are here screen | 1) Verification of moqup | 1) Moqup - Home screen | 1) Moqup - Verification
| 2) Created moqup for you are here screen | 2) Verified the moqup | 2) Created the moqup - home screen in tablet background | 2) Verified the moqup | 2) Uploaded the moqup to GIT
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Vamsee Krishna Solasa | 1) Scope Document Issue Management | 1) Test case document - Verification | 1) Testcase document - verification | 1) Use case diagram - helped | 1) requirement document creation - help
| 2) Veried the moqup | 2) Verified the test case document | 2) Helped with Use case diagram | 2) Helped with the requirement document creation | 2) Verified and uploaded the Issues managemetn file to GIT
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?

## Oct31-Nov4
Daily Stand-up Meeting Report
Week: Oct31-Nov4
Project Name: Campus Cruise
Team Name: Crazy Coders
| Monday | Tuesday | Wednesday | Thursday | Friday
Nayan Reddy Prodduturi | 1) Discussed on the home screen | 1) Created template | 1) Took Scenarios and convert them to use manual scenarios | 1) Created user manual | 1) User manual refinement
| 2) Learned android tutorial. | 2) Learned android tutorial. | 2) Edited the installation guide. | 2) Learned android tutorial. | 2) Learned android tutorial.
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Mallikharjuna Rao Dande | 1) Requirement discovery forgot password | 1) requirement discovery offline maps | 1) requirement discovery offline maps | 1) worked on installation document | 1) worked on user manual
| 2) Use case diagram for forgot password | 20 use case diagram for offline maps | 2) Worked on Installation document | 2) Worked on User Manual | 2) Worked on Installation document
| 3) no issues | 3) no issues | 3) no issues | 3) Need reliable source for gathering he source of the map data | 3) No issues
Chiranjeevi Sneha Kotu | 1) Discussed on the home screen | 1) Created backgroud to use for moqup | 1) Createed moqup | 1) Verifeid Use case diagrams | 1) Requirement management document
| 2) Created backgroud to use for moqup | 2) Collaborated with team to create a moqup for different screens | 2) Verifed hte use case diagram | 2) Verifeid hte requirement management document | 2) verified the issues management document
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Teja Parimi | 1) Test cases and test plan development | 1) Test cases and test plan development | 1) Test cases and test plan development | 1)Test cases and test plan development | 1) Test cases and test plan development
| 2) Test cases and test plan development | 2) Test cases and test plan development | 2) Test cases and test plan development | 2) Test cases and test plan development | 2) Test cases and test plan development
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Rakesh Chitturi | 1) Pepared Gantt Chart | 1) Pepared Gantt Chart | 1) Pepared Gantt Chart | 1) Pepared Gantt Chart | 1) Pepared Gantt Chart
| 2) Pepared Gantt Chart | 2) Pepared Gantt Chart | 2) Pepared Gantt Chart | 2) Pepared Gantt Chart | 2) uploaded to Gantt Chart
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Vamsee Krishna Solasa | 1) Updated the issue management tracker | 1) Verify the documents uploaded | 1) Preparing and working on all the documents of end term presentation. | 1) Android tutorials | 1) Preparing and working on all the documents of end term presentation.
| 2) Worked on gathering information for the end semester presentation | 2) Update and upload the issue management tracker on GIT | 2)Working with the group to ensure documents are ready for the end term presentation | 2) Verified all the documents | 2) Verified,updated and uploaded the Issues managemetn file to GIT
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?

## Nov7-Nov11
Daily Stand-up Meeting Report
Week: Nov7-Nov11
Project Name: Campus Cruise
Team Name: Crazy Coders
| Monday | Tuesday | Wednesday | Thursday | Friday
Nayan Reddy Prodduturi | 1) Preparing and working on all the documents of end term presentation. | 1) Preparing and working on all the documents of end term presentation. | 1) Preparing and working on all the documents of end term presentation. | 1) Preparing and working on all the documents of end term presentation. | 1) Preparing and working on all the documents of end term presentation.
| 2) Working on test cases. | 2) Working on test cases. | 2) Help with use case diagrams. | 2) Working with group and getting all the documents ready. | 2) Working with group and getting all the documents ready.
| 3) No Issues | 3) Issue may arise with the Mbaas provider failure | 3) No Issues | 3) working on potential solution to the mbaas failure | 3) we can store partial information in the app when it first connects to database and save it locally and download details in need to use basis to reduce total dependency on the online database for basic functionality.
Mallikharjuna Rao Dande | 1) Use Case diagram Map | 1) Use case diagram Super user | 1) Usecase diagam DBA | 1) Requirement discovery Database Adminstration | 1) Requirement discovery virtual tour
| 2) worked on specifications document | 2) Worked on use case diagrams for virtual tour | 2) worked on use case diagrams for virtual tour | 2) worked on specifications document | 2) Worked on Specifications document
| 3) no issues | 3) no issues | 3) no issues | 3) Need reliable source for gathering he source of the map data | 3) No issues
Chiranjeevi Sneha Kotu | 1) Preparing and working on all the requirments for the end term presentation | 1) Preparing and working on all the requirments for the end term presentation | 1) Preparing and working on all the requirments for the end term presentation | 1) Preparing and working on all the requirments for the end term presentation | 1) Preparing and working on all the requirments for the end term presentation
| 2) Working with group and getting all the documents ready and uploading on git hub and working collaboratively checking all the works | 2) Working with group and getting all the documents ready and uploading on git hub and working collaboratively checking all the works | 2) Working with group and getting all the documents ready and uploading on git hub and working collaboratively checking all the works | 2) Working with group and getting all the documents ready and uploading on git hub and working collaboratively checking all the works | 2) Working with group and getting all the documents ready and uploading on git hub and working collaboratively checking all the works
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Teja Parimi | 1) Scope document - Test case document | 1) Android tutorial | 1) Created test case - distance between buildings | 1) Test case - Data connection lost | 1) Test case - Approaching a document
| 2) Did android tutorial | 2) Created test case - Distance between buildings | 2) Created a test case - Data connection lost | 2) Created test cases - Appraoching a building | 2) Verifed the test case document
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Rakesh Chitturi | 1) worked on data management plan document | 1) worked on data management plan document | 1) worked on data management plan document | 1) worked on data management plan document | 1) worked on data management plan document
| 2)worked on data management plan document | 2) worked on data management plan document | 2) worked on data management plan document | 2) worked on data management plan document | 2) Uploaded to github
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Vamsee Krishna Solasa | 1) Scope Document Issue Management | 1) Test case document - Verification | 1) Testcase document - verification | 1) Use case diagram - helped | 1) requirement document creation - help
| 2) Veried the moqup | 2) Verified the test case document | 2) Helped with Use case diagram | 2) Helped with the requirement document creation | 2) Verified and uploaded the Issues managemetn file to GIT
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?

## Nov14-Nov18
Project Name: Campus Cruise
Team Name: Crazy Coders
| Monday | Tuesday | Wednesday | Thursday | Friday
Nayan Reddy Prodduturi | 1) | 1) | 1) | 1) | 1)
| 2) | 2) | 2) | 2) | 2)
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Mallikharjuna Rao Dande | 1) Specifications Document | 1) Change Management Plan | 1) Worked on the end semester presentation | 1) Worked on additional use cases | 1) Project management plan
| 2) Change Management Plan | 2) Work on the end semester presentation | 2) client approval for the requirement completion. | 2) Project management plan | 2) Cost Analysis
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Chiranjeevi Sneha Kotu | 1) | 1) | 1) | 1) | 1)
| 2) | 2) | 2) | 2) | 2)
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Teja Parimi | 1) | 1) | 1) | 1) | 1)
| 2) | 2) | 2) | 2) | 2)
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Rakesh Chitturi | 1) | 1) | 1) | 1) | 1)
| 2) | 2) | 2) | 2) | 2)
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Vamsee Krishna Solasa | 1) | 1) | 1) | 1) | 1)
| 2) | 2) | 2) | 2) | 2)
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?

## Nov21-Nov22
Project Name: Campus Cruise
Project Name: Campus Cruise
Team Name: Crazy Coders
| Monday | Tuesday | Wednesday | Thursday | Friday
Nayan Reddy Prodduturi | 1) | 1) | 1) | 1) | 1)
| 2) | 2) | 2) | 2) | 2)
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Mallikharjuna Rao Dande | 1) Cost Analysis | 1) Generated Test Plan document template | 1) Generated test plan roles and responsibilites | 1) Generated test plan schedule | 1) Worked on scenarios fro Test suite
| 2) Generated Test Plan document template | 2) Generated test plan roles and responsibilites | 2) Generated test plan schedule | 2) Worked on scenarios fro Test suite | 2) Write Test Suite
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Chiranjeevi Sneha Kotu | 1) | 1) | 1) | 1) | 1)
| 2) | 2) | 2) | 2) | 2)
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Teja Parimi | 1) | 1) | 1) | 1) | 1)
| 2) | 2) | 2) | 2) | 2)
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Rakesh Chitturi | 1) | 1) | 1) | 1) | 1)
| 2) | 2) | 2) | 2) | 2)
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Vamsee Krishna Solasa | 1) | 1) | 1) | 1) | 1)
| 2) | 2) | 2) | 2) | 2)
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?

## Nov28-Dec2
Project Name: Campus Cruise
Project Name: Campus Cruise
Team Name: Crazy Coders
| Monday | Tuesday | Wednesday | Thursday | Friday
Nayan Reddy Prodduturi | 1) | 1) | 1) | 1) | 1)
| 2) | 2) | 2) | 2) | 2)
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Mallikharjuna Rao Dande | 1) Work on Test Suite | 1)New Usecases: University DBA | 1) New Usecase: Forgot password | 1) New Usecase: QR and GPS | 1) Update requirements document with new usecases
| 2) New Usecases: University DBA | 2) New Usecase: Forgot password | 2) New Usecase: QR and GPS | 2) Update requirements document with new usecases | 2) Update requirements document with new usecases
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Chiranjeevi Sneha Kotu | 1) | 1) | 1) | 1) | 1)
| 2) | 2) | 2) | 2) | 2)
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Teja Parimi | 1) | 1) | 1) | 1) | 1)
| 2) | 2) | 2) | 2) | 2)
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Rakesh Chitturi | 1) | 1) | 1) | 1) | 1)
| 2) | 2) | 2) | 2) | 2)
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Vamsee Krishna Solasa | 1) | 1) | 1) | 1) | 1)
| 2) | 2) | 2) | 2) | 2)
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?

## Dec5-Dec9
Project Name: Campus Cruise
Project Name: Campus Cruise
Team Name: Crazy Coders
| Monday | Tuesday | Wednesday | Thursday | Friday
Nayan Reddy Prodduturi | 1) | 1) | 1) | 1) | 1)
| 2) | 2) | 2) | 2) | 2)
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Mallikharjuna Rao Dande | 1) Working on Final artifact submission | 1) Requirement document enhancement | 1) Worked on all documents for submission | 1) | 1)
| 2) Requirement enhancement : Virtual tour | 2) Worked on all documents for submission | 2) Presentation feedback | 2) | 2)
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Chiranjeevi Sneha Kotu | 1) | 1) | 1) | 1) | 1)
| 2) | 2) | 2) | 2) | 2)
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Teja Parimi | 1) | 1) | 1) | 1) | 1)
| 2) | 2) | 2) | 2) | 2)
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Rakesh Chitturi | 1) | 1) | 1) | 1) | 1)
| 2) | 2) | 2) | 2) | 2)
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Vamsee Krishna Solasa | 1) | 1) | 1) | 1) | 1)
| 2) | 2) | 2) | 2) | 2)
| 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues | 3) No Issues
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?